## Office of Special Events | Event Planning Checklist

Plan Your Event with Confidence – 6–9 Month Timeline

### 6-9 Months Before the Event

- ☐ Define the purpose and goals of your event

- ☐ Identify your target audience (students, faculty, staff, community, etc.)

- ☐ Determine a preferred date & alternate date in parenthesis (be flexible)

- ☐ Reserve your event space through the Office of Events https://www.myccp.online/strategic-communications/form/event-request-form

- ☐ Determine your budget and secure funding if needed

- ☐ Start brainstorming your theme or concept

- ☐ Create a planning team or assign roles (logistics, promotions, etc.)

- ☐ Research vendors if applicable

- ☐ Begin event proposal/approval process (if required)

### 4-6 Months Before the Event

- ☐ Finalize venue and confirm with the Office of Events

- ☐ Begin outlining your program or agenda

- ☐ Confirm speakers, performers, or special guests

- ☐ Request the President to speak at high profile engagements. https://www.myccp.online/strategic-communications/form/request-president-form

- ☐ Submit necessary work orders (custodial, security, tech support)

- ☐ Request catering estimates and begin menu planning

- ☐ Design event logo or branding if needed

- ☐ Develop an initial promotion strategy

- ☐ Create RSVP or registration form (if applicable)

### 2-3 Months Before the Event

- ☐ Request form

- ☐ Launch event marketing campaign (flyers, email, social media)

- ☐ Confirm all vendor contracts (catering, rentals, etc.)

- ☐ Submit work orders for setup, HVAC and housekeeping through the FAMIS work order system.

- ☐ Begin collecting RSVPs or registrations

- ☐ Order promotional materials, swag, or signage

- ☐ Coordinate with campus partners (student orgs, departments)

- ☐ Finalize room setup, A/V, and technical needs

- ☐ Begin drafting your event script or run-of-show

### 1 Month Before the Event

- ☐ Reconfirm all vendors, speakers, and logistics

- ☐ Schedule final walkthrough with the Office of Special Events

- ☐ Send out reminder emails and push final promotions

- ☐ Prepare event materials (agendas, name tags, welcome kits)

- ☐ Assign volunteer/staff roles for the day of event

- ☐ Print signage and materials

### 1 Week Before the Event

- ☐ Conduct final team meeting and walkthrough

- ☐ Prepare event supplies and emergency kit

- ☐ Confirm headcount with caterers and vendors

- ☐ Print a copy of this checklist for day-of use

- ☐ Send final reminders to attendees

- ☐ Send final copy of attendees to office of events for security

### Day of Event

- ☐ Arrive early for setup

- ☐ Complete a walkthrough with team

- ☐ Set up registration/check-in area

- ☐ Test all A/V and technology

- ☐ Welcome guests and stay on schedule

- ☐ Troubleshoot and enjoy!

### Post-Event

- ☐ Send thank-you emails to speakers, volunteers, and vendors

- ☐ Collect feedback from attendees- all college survey's must be initiated through the Office of Institutional Effectiveness

- ☐ Return rented items

- ☐ Meet with team to debrief and document notes for next time

- ☐ Submit final report (if applicable)

For questions, reservations, or to speak with our event team:

Email: eharrison@ccp.edu| jali@ccp.edu